## ISO 9001 2015
TAHAPAN BIMBINGAN KONSULTASI IMPLEMENTASI SISTEM MANAJEMEN MUTU STANDAR ISO 9001:2015 & SISTEM MANAJEMEN LINGKUNGAN STANDAR ISO 14001:2018
NAMA PERUSAHAAN |  | : PT. SENJAYA ECO KASEI
LOKASI |  | : Jl. Pinang Blok F.20 No. 16 C-D Kawasan Industri Delta Silicon 3 Bekasi
NO. PROPOSAL |  | : 014/STM/MKT-SPK/II/26
NO | Tahapan | PIC Sentral Sistem | Dept. Terkait | PIC PT. SENJAYA | Mandays | Status | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | Mei |  |  |  | Jun
[7 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Kick Off & Gap Analysis Discuss with BOD and All Management (Each Process Owner) --> concern about the expectations of the Program of Environmental Management System, Current conditions in implementing the Quality and Environmental Management System and other systems | Bpk. Immanuel Iman & Angga | All Dept | All Dept | 2 | Plan | Feb 2: 12; Feb 3: 16
[6 empty] | Actual | Feb 2: 12; Feb 3: 16
2 | Training on Business Process Mapping (BPM) | Angga | All Dept | All Dept | 1 | Plan | Feb 4: 26
[6 empty] | Actual | Feb 4: 26
3 | Executive Briefing and Consultation of Business Process Mapping (BPM) Identify Organizations and Its Contex, included Interested parties in relation to Organization and Its Contex- Identification of Legislation & Environmental Requirements (related to Business, Product and Environment) | Angga | MR/Related Function | Pak Joshua | 1 | Plan | Feb 4: 27
[6 empty] | Actual | Feb 4: 27
4 | Training on Awareness of Integrated Requirement of ISO 9001:2015 and ISO 14001:2015 | Angga | All Dept | All Dept |  | Plan | Mar 1: 3
Actual
4 | GAP Anaysis ISO 14001 | Dhiwa | All Dept | All Dept | 1 | Plan | Mar 1: 3
[6 empty] | Actual | Mar 1: 3
4 | Training on Awareness of Integrated Requirement of ISO 9001:2015 and ISO 14001:2015 | Angga | All Dept | All Dept | 1 | Plan | Mar 1: 4
[6 empty] | Actual | Mar 1: 4
5 | Consultation of Integrated ISO 9001 - ISO 14001 Risk Identification - Opportunities for: Documented Information process/ document control, record control, backup data, work instruction format & check sheet | Angga | Doc Control / Related Dept |  | 1 | Plan | Mar 1: 3
[6 empty] | Actual | Mar 1: 3
6 | Consultation of Integrated ISO 9001 - ISO 14001 Risk Identification - Opportunities for: Recruitment and training process opportunities + Competency standards + Job Desc | Angga | HR | Pak Wahyu |  | Plan | Mar 1: 3
[6 empty] | Actual | Mar 1: 3
7 | Training on Identification of Environmental Aspect -Impacts Workshop: - Identification of Aspects and Environmental Impacts Assessment - Identify Other Risks and Environmental Opportunities | Amdani | All Dept | All Dept | 1 | Plan | Mar 2: 10
[6 empty] | Actual | Mar 2: 10
8 | Consultation (using ISO 14001:2015 guidelines): - Identification of Environmental Aspect-Impact in each area - Life Cycle Perspectives | Amdani | Related Function | Pak Wahyu | 3 | Plan | Apr 1: 2
[6 empty] | Actual | Apr 1: 2
9 | Consultation of Integrated ISO 9001 - ISO 14001 Risk identification - Opportunities for: Sales process, customer-owned products, customer satisfaction | Angga | Sales | Ohtani San | 1 | Plan | Mar 3: 16
[6 empty] | Actual | Mar 3: 16
10 | Consultation of Risks Identification - Opportunities for:Billing and Payment | Amdani | Finance & Accounting | Pak Agung |  | Plan | Mar 3: 16
[6 empty] | Actual | Mar 3: 16
11 | Organizational Risk Completion Review: - Organizational Context - Business process mapping (BPM) and SIPOCORR (Supplier- Input-Process-Output-Customer-Objectives-Risk-Reference) - Identification of Legislation & Other Requirements (related to Business, Quality, and Environment) | Angga | MR/Related Function | Pak Joshua | 1 | Plan | bar: Mar 4 to Apr 1
[6 empty] | Actual | Mar 2: 12; Apr 1: 1
12 | Review of completion of Integrated of ISO 9001 - ISO 14001 for Documented Information/document control processes, record control, backup data, work instruction, standard formats & check sheet | Amdani | Doc Control / Related Dept |  | 1 | Plan | bar: Apr 1
Actual | bar: Apr 1
13 | Review completion of Integrated of ISO 9001 - ISO 14001 for recruitment and training + Competency standards + Job Desc processes | Angga | HR | Pak Wahyu | 1 | Plan | Apr 1: 2
[6 empty] | Actual | Mar 3: 16
14 | Consultation of Integrated ISO 9001 - ISO 14001 Identification of Risks and Opportunities for: - Production Planning Process - Material Handling Process - Procurement Process / Purchase, Control of sub cont --> JEA, Environment Induction, MSDS, Chemical substance - Product Design - PPE Contro | Amdani | PPIC Purch | Purch : Pak Anggi / Pak Laranru / Pak Wahyu | 1 | Plan | Apr 1: 2
[6 empty] | Actual | Mar 3: 16; Apr 1: 2
15 | Review completion of Integrated of ISO 9001 - ISO 14001 for: Sales process, customer-owned products, customer satisfaction | Angga | Sales | Ohtani San | 1 | Plan | Mar 4: 7; Apr 1: 7
Actual | bar: Apr 1
16 | Review and Completion Risks - Opportunies for: for:Billing and Payment | Amdani | Finance & Accounting | Pak Agung |  | Plan | Mar 4: 7; Apr 1: 7
[6 empty] | Actual | Mar 3: 16
17 | Consultation of Integrated ISO 9001 - ISO 14001 Identification of Risks and Opportunities for: - Production process and checking - Nonconformity product control - Standard special characteristics - Standard line stop criteria - Standard setting, production work instructions & check sheet | Angga | Prod QC | Prod : Mr. Suksun QC : Bu Windi | 1 | Plan | Apr 1: 8
[6 empty] | Actual | Mar 3: 16
18 | Training on Hazardous and Hazardous Waste Management | Amdani | All Dept | All Dept | 1 | Plan | Apr 2: 14
Actual
18 | Training on Hazardous and Hazardous Waste Management | Amdani | All Dept | All Dept | 1 | Plan | Apr 2: 13
[6 empty] | Actual | Apr 2: 13
19 | Consultation on Hazardous and Hazardous Waste Control, Environmental Monitoring and Measurement | Amdani | Related Function | Pak Wahyu | 1 | Plan | Apr 2: 15
[6 empty] | Actual | Mar 2: 11
20 | Consultation of Integrated ISO 9001 - ISO 14001 Identification of Risks and Opportunities for: - Warehouse Process - Delivery Process | Angga | WH Delivery | Pak Wahyu(2) | 1 | Plan | Apr 3: 21
[6 empty] | Actual | Apr 1: 2
21 | Consultation of Integrated ISO 9001 - ISO 14001 Risk Identification - Opportunity for: - Infrastructure Maintenance Process - Infrastructure Improvement Process - Control of measuring test and calibration equipment | Angga | GA Maintenance QC | GA : Pak Wahyu HR Maint : Pak Dimas QC : Bu Windi |  | Plan | Apr 3: 21
Actual | bar: Apr 2
22 | Review Completion of Identification of Environmental Impact Aspects (IADL) 1. Results of Identification of Aspects and Assessment of Environmental Impact 2. Identification of Aspects and Opportunities within the Company Management System - Life Cycle Perspective | Amdani | Related Function | Pak Wahyu | 1 | Plan | Apr 3: 22
Actual
22 | Review Completion of Identification of Environmental Impact Aspects (IADL) 1. Results of Identification of Aspects and Assessment of Environmental Impact 2. Identification of Aspects and Opportunities within the Company Management System - Life Cycle Perspective | Amdani | Related Function | Pak Wahyu | 1 | Plan | Apr 3: 24
[6 empty] | Actual | Apr 3: 24
23 | Review completion of Integrated of ISO 9001 - ISO 14001 for: - Production Planning Process - Material Handling Process - Procurement Process / Purchase, Control of sub cont --> JEA, Environment Induction, MSDS, Chemical substance - Product Design, - PPE Control | Amdani | PPIC Purch | Prod : Mr. Suksun Purch : Pak Anggi & Ohtani San | 1 | Plan | Apr 3: 24
[6 empty] | Actual | Apr 3: 24
25 | Review completion of Integrated of ISO 9001 - ISO 14001 for - Warehouse Process - Delivery Process | Angga | WH Delivery | WH Pak Wahyu (2) | 1 | Plan | Apr 4: 28
[6 empty] | Actual | Apr 4: 28
26 | Review completion of Integrated of ISO 9001 - ISO 14001 for processes of: - Infrastructure Maintenance Process - Infrastructure Improvement Process - Control of measuring test and calibration equipment | Angga | GA Maintenance QC | GA : Pak Wahyu HR Maint : Pak Dimas QC : Bu Windi |  | Plan | Apr 4: 28
[6 empty] | Actual | Apr 4: 28
29 | Consultation of ISO 14001 Risk Identification - Opportunity for: - Process of Communication, | Amdani | Related Function | Pak Wahyu | 1 | Plan | Mei 1: 4
[6 empty] | Actual | Apr 4: 29
30 | Consultation of ISO 14001 Risk Identification - Opportunity for: - Emergency Preparedness & Response Process - Regarding the Spill - Regarding Pollution / Overflow - Other Potential Emergencies | Amdani | Related Function | Pak Wahyu |  | Plan | Mei 1: 4
[6 empty] | Actual | Apr 1: 1; Apr 4: 29
31 | Review completion of Integrated of ISO 9001 - ISO 14001 for: - Emergency Preparedness & Response Process - Regarding the Spill - Regarding Pollution / Overflow - Other Potential Emergencies;Review completion of Integrated of ISO 9001 - ISO 14001 for processes of: - Customer Claims - Corrective actions - Incident Investigation & Report - Continuous improvement;Review completion of Integrated of ISO 9001 - ISO 14001 for: - Policy of Quality - Environment - Target Company Quality - Environment - Activity Plan Quality - Environment - Quality Plan Business Process - Environment - Quality Management Review - Environment | Amdani | Related Function | Pak Wahtu | 2 | Plan | Mei 1: 6; Mei 3: 18
[6 empty] | Actual | Mei 1: 6; Mei 3: 18
32 | Training on Internal Audit Integrated ISO 9001:2015 and ISO 14001:2015 Based on Risk and Performance of ISO 19011:2018 | Angga | All Dept | All Dept | 2 | Plan | Mei 3: 11 & 12
[6 empty] | Actual | Mei 3: 11 & 12
24 | Review completion of Integrated of ISO 9001 - ISO 14001 for - Production process and checking - Nonconformity product control - Standard special characteristics - Standard line stop criteria - Standard setting, production work instructions & check sheet | Angga | Prod QC | Prod : Mr. Suksun QC : Bu Windi | 1 | Plan | Mei 3: 19
[6 empty] | Actual | Mei 3: 19
27 | Consultation of Integrated ISO 9001 - ISO 14001 Risk Identification - Opportunity for: - Customer Claims - Corrective actions - Incident Investigation & Report - Continuous improvement | Angga | MR/Related Function | Pak Joshua | 1 | Plan | Mei 3: 19
[6 empty] | Actual | Mei 3: 19
28 | Consultation of Integrated ISO 9001 - ISO 14001 Risk Identification - Opportunity for: - Policy of Quality - Environment - Target Company Quality - Environment - Activity Plan Quality - Environment - Quality Plan Business Process - Environment - Quality Management Review - Environment | Angga | MR/Related Function | Pak Joshua |  | Plan
Actual
33 | Internal Audit Integrated by Client | Angga dan Amdani | All Dept | All Dept | 0 | Plan | bar: Mei 3
Actual
34 | Internal Audit Integrated by Consultant |  | All Dept | All Dept | 2 | Plan | Mei 4: 21 & 22
Actual
35 | Corrective Action Integrated for Audit Consultant & Preparation for Stage 1 Eksternal Audit | Angga dan Amdani | All Dept | All Dept | 1 | Plan | Jun 1: 2
Actual
36 | Audit Stage 1 by Certification Body | Badan Sertifikasi | All Dept | All Dept |  | Plan | bar: Jun 2
Actual
37 | Corrective Action for Stage 1 | Angga dan Amdani | All Dept | All Dept | 1 | Plan | bar: Jun 2
Actual
38 | Audit Stage 2 by Certification Body | Badan Sertifikasi | All Dept | All Dept |  | Plan | bar: Jun 4
Actual | bar: Jun 4
39 | Corrective Action for Stage 2 & Closing Project | Angga dan Amdani | All Dept | All Dept | 1 | Plan
Actual | bar: Jun 4
| Total |  |  |  | 38
Belum Termasuk PPN 11% , Makan Siang Konsultan, Biaya Sertifikasi ke Badan Sertifikasi
Bisnis Logistik
SGS
BSI
TUV SUD
Investasi Sudah Termasuk :
Spanduk dan standing banner untuk sosialisasi program 1 buah
Swab Antigen test konsultan saat ke LOKASI bila diperlukan
Materi Training dan E-Certificate untuk 20 peserta yg bisa divalidasi ke www.sentralsistem.com Client Area - Sentral Sistem
Note on I8: Asus A442UR: Kick Off
Note on J8: Asus A442UR: GAP Analysis ISO 9001 : 16 Frb GAP Analysis ISO 14001 : 20 Feb
Note on P27: Asus A442UR: MTC, PRD , WH sudah